## Slide 1: Unit 3 Project management techniques
By Prof Aarti Vyas

## Slide 2: Program Evaluation and Review Technique Analysis (PERT)
In project management, the Project Evaluation Review Technique, or PERT, is used to identify the time it takes to finish a particular task or activity.
It is a system that helps in proper scheduling and coordination of all tasks throughout a project. It also helps in keeping track of the progress, or lack thereof, of the overall project.
In the 1950s, the Project Evaluation Review Technique was developed by the US Navy to manage the Polaris submarine missile program of their Special Projects Office.
PERT chart will help determine realistic estimates.

## Slide 3: Four terms used for creating Pert Chart
Optimistic time – The least amount of time it can take to complete a task
Pessimistic time – The maximum amount of time it should take to complete a task
Most likely time – Assuming there are no problems, the best, or most reasonable, estimate of how long it should take to complete a task.
Expected time – Assuming there are problems, the best estimate of how much time will be required to complete a task.

## Slide 4
Float/Slack – Refers to the amount of time a task can be delayed without resulting in an overall delay in completion of other tasks or the project
Critical Path – Indicates the longest possible continuous path from the start to the end of a task or event
Critical Path Activity – Refers to an activity without any slack
Lead Time– Refers to the amount of time needed to finish a task without affecting subsequent tasks
Lag Time – The earliest time by which a successor event/task can follow a prior event/task
Fast Tracking – Refers to handling tasks or activities in parallel
Crashing Critical Path – Shortening the amount of time to do a critical task

## Slide 5: Advantages of PERT
Here are several benefits of using PERT in project management:
It helps maximize the use of resources.
It makes project planning more manageable.
It’s useful even if there is little or no previous schedule data.
It enables project managers to better estimate or determine a more definite completion date.

## Slide 6: Disadvantages of PERT
Like any other method, PERT comes with its share of limitations:
In complex projects, many find PERT hard to interpret, so they may also use a Gantt Chart, another popular method for project management. It can be tedious to update, modify, and maintain the PERT diagram
It entails a subjective time analysis of activities and, for those who are less experienced or are biased, this may affect the project’s schedule

## Slide 7: PERT
The PERT assumes that the activity duration is not fixed and it follows a certain probability distribution
The technique of PERT was developed by US Navy 1958 for the Polaris missile programme
CPM Critical part method
It assumes that an activity can be completed with in the specified time
This technique was developed b E I DU Pont de NEMOURS and Co 1957
For the construction of new chemical palnt and maintenance shut down

## Slide 8: PERT and CPM
How long will the entire project take to be completed
What are the risk involved
Which are the critical activities or tasks in the project which could delay the entire project if they were not completed on time
Is the project on schedule behind schedule or ahead of schedule
If the project has to be finished earlier than palnned what is the best way to do this at he least cost

## Slide 9: Objective of Network Analysis
To establish relationship between various activities in a project
To minimize project cost
To minimize the project completion time
To ensure optimum utilization of human and other resources
To ensure minimum conflicts and unnecessary delays

## Slide 10: Basic concepts of Network analysis
Activity – An activity is a task scheduled to be completed within a specific expected duration of time
Event an event represents the starting and ending point of the activity
The two end of the activity are referred as start (Head) and End (Tail) node always denoted by numbers in a logical order
Analysis of the Daigram The activity A may be represented by node 1 and
A
Start Node
End Node

## Slide 11: Basic concepts of Network analysis
Path - Path refers to the sequence of activities that complete the project in the specific period of time there are various paths/routes in which the project can be completed
Critical path It is the longest path in terms of project completion time by which the project is completed
The activities on the critical path are called the critical activites The completion of these activities cannot be delayed

## Slide 12: Basic concepts of Network analysis
When two or more activates are sequential in nature if the end of one activity is the start of the another such situation is known as Sequential activities
For Example Activity Q starts after Activity P
8 2
Q
P

## Slide 13
Preceding or Predecessor Activity
It is an activity that must be completed prior to the start of another activity
A B
5 4
Activity A proceed Activity B

## Slide 14
Succeeding or Successor Activity
It is the Activity that cannot be started till one or more preceding activities are complete
E F
5 3
Activity F Succeeds activity E

## Slide 15
Concurrent Activites
Activates that can be performed simultaneously at the same time are called concurrent activities
Q 3
P
1 2
R 4

## Slide 16
Merge Event Brust Event
An event which represents completion of multiple activities is known as a merge event
3
R
5 4
5
4
Brust Event represents the start of multiple activities is called burst event

## Slide 17: Critical Path Method
Critical Event refers to an event in the project which cannot be delayed by any time duration beyond its earliest occurrence time without affecting the total projet completion time
Critical activity refers to an activity in which the starting or completion time cannot be delayed without affecting the total project completion time

## Slide 18
Critical path is the longest path in the network diagram the path with the maximum duration
Any delay along the critical path will result in delaying the total project completion time

## Slide 19: Advantages of CPM
It helps in ascertaining the time schedule of activities having sequential relationship
It makes control easier for the management
It identifies the most critical elements is the project thus helping the management to pay attention on the critical activities
It makes better and detailed planning possible

## Slide 20: Disadvantage of CPM
CPM operates on the assumption that there is a precise known time that each activity in the project will take But it may not be true in real life
CPM time estimates are not based on statistical analysis
It cannot be used as controlling device since any change introduced will change the entire structure of the network Thus CPM cannot be used as a dynamic controlling device

## Slide 21: Construct a network diagram of the following
Activity Duration in days
1-2 5
2-3 3
2-4 2
2-5 1
3-6 4
4-8 6
5-7 5
6-8 7
7-8 2

## Slide 23: Sum no 2
Activity Predecessor Activity
A None
B None
C A
D A
E B
F C
G D and E